UMGC CMSC 495

Computer Science Capstone

Personal Expense Tracker

Project Plan

Submitted by:

Jamar (Project Manager)

Matthew (Lead Developer)

Kyle (UI/Frontend Developer)

Joe (QA Tester / Developer)

Mayank(UI/Frontend Developer)

Greg(QA Tester / Developer)

Spring 2026

March 15, 2026

# 1. Executive Summary

The Personal Expense Tracker is a desktop application developed as part of the UMGC CMSC 495 Computer Science Capstone course. The application will be built using Java as the primary programming language, with Python used for supplementary data import/export scripting. The goal of this project is to provide individual users with a simple, intuitive, and effective tool to record, categorize, and analyze their personal financial expenditures.

The application will allow users to log daily expenses, assign them to predefined or custom categories (e.g., Food, Transportation, Entertainment), and generate summary reports and visual breakdowns of their spending habits over time. All data will be stored locally using a lightweight SQLite database, ensuring privacy and offline accessibility.

This project plan outlines the team structure, project scope, goals, resources, schedule, communication strategy, and risk management approach that will guide the development of this application from inception through final delivery on May 5, 2026.

# 2. Project Overview

Managing personal finances is a challenge that affects a wide range of individuals. Many people lack a structured, accessible way to track day-to-day spending, which can lead to poor budgeting decisions and financial stress. While numerous commercial tools exist, they often require internet connectivity, subscriptions, or complex setups that deter casual users.

The Personal Expense Tracker addresses this gap by delivering a self-contained desktop application with a graphical user interface (GUI) that requires no internet connection and no subscription. The application is designed to be straightforward and user-friendly, targeting students, young professionals, and anyone looking to take control of their spending without relying on cloud-based services.

The project will be developed across four phases: initial planning and design, core feature development, enhancement and refinement, and final testing and documentation. The team of four will collaborate using GitHub for version control, weekly Zoom meetings for alignment, and UMGC's LEO platform for course-related submissions and communication.

The application will be delivered as a runnable desktop program, accompanied by user documentation and a final presentation to stakeholders.

# 3. Project Goals and Objectives

## 3.1 Primary Goal

To design, develop, test, and deliver a fully functional Personal Expense Tracker desktop application that meets the course requirements and demonstrates the team's ability to apply software engineering principles in a collaborative capstone project.

## 3.2 Objectives

- Develop a working desktop GUI application using JavaFX.

- Implement core features: expense entry, categorization, editing, deletion, and search.

- Implement a local SQLite database to persist expense records between sessions.

- Provide visual summary reports (bar/pie charts) of spending by category and time period.

- Enable CSV/JSON import and export functionality using Python scripting.This integration will be orchestrated via Java’s ProcessBuilder API, which allows the application to execute scripts as independent system processes, ensuring a clean architectural separation between the core logic and supplementary data utilities.

- Produce complete project documentation including a user guide and test plan.

- Deliver a final presentation on May 5, 2026 to course stakeholders.

## 3.3 Deliverables

- Project Plan (Due: March 18, 2026)

- Project Design Document

- Source Code and Source Code Outline

- User Guide and Test Plan

- Fully functional Personal Expense Tracker application

- Final Report (Due: May 5, 2026)

# 4. Project Scope

## 4.1 In Scope

The following features and functions are included in the project:

- User registration and login (local, no internet required)

- Ability to add, edit, and delete expense records with date, amount, category, and description

- Predefined expense categories (Food, Transportation, Housing, Entertainment, Healthcare, Other) with the ability to add custom categories

- Dashboard displaying a summary of recent and monthly expenses

- Graphical spending reports (bar and pie charts) filterable by date range and category

- Search and filter functionality across expense records

- Data export to CSV and JSON formats via Python script

- Data import from CSV to pre-populate expense records

- Local SQLite database for offline data persistence

- User documentation and in-app help reference

- System monitoring

- Containerization of applications

## 4.2 Out of Scope

The following items are explicitly excluded from this project:

- Cloud storage or online synchronization of expense data

- Mobile application development (iOS or Android)

- Integration with external banking APIs or financial institutions

- Multi-user or shared account functionality

- Subscription billing or payment features

- Automated recurring expense tracking

## 4.3 Assumptions and Constraints

- All team members have access to a personal computer capable of running Java applications.

- The project must be completed by May 5, 2026, the course's final deadline.

- The application will be developed for Windows, with best-effort compatibility for macOS and Linux.

- No external budget is required; all tools and libraries used are free and open-source.

# 5. Project Resources

## 5.1 Team Roles and Responsibilities

| Member | Role | Responsibilities |
| --- | --- | --- |
| Jamar | Project Manager / Developer | Leads team coordination, tracks milestones, contributes to core development and oversees final report. |
| Matthew | Lead Developer | Leads backend logic development, data persistence layer, and Java/Python integration. |
| Kyle, Mayank | UI / Frontend Developer | Designs and implements the desktop GUI, ensuring a clean and intuitive user experience. |
| Joe, Greg | QA Tester / Developer | Develops test cases, performs quality assurance, and contributes to feature development. |

## 5.2 Tools and Technologies

| Resource | Type | Description |
| --- | --- | --- |
| Jamar, Matthew, Kyle, Joe, Mayank, Greg | Personnel | 4 team members contributing design, development, testing, and documentation. |
| Java JDK / JRE | Software | Primary language for core application logic and desktop GUI development (JavaFX / Swing). |
| Python | Software | Supplementary scripting: data import/export (CSV/JSON) and report generation. |
| SQLite | Software | Lightweight embedded database for local storage of expense records. |
| GitHub | Tool | Version control and collaboration; all members commit to a shared repository. |
| Zoom / Discord | Communication | Weekly virtual team meetings and ad-hoc collaboration. |
| Personal Computers | Hardware | Each member uses their own development machine (Windows/macOS/Linux). |
| UMGC LEO | Platform | Course submission portal, shared resources, and instructor communication. |

## 5.3 Project Schedule

The table below provides an overview of key project milestones and their target dates. All team members are expected to contribute to each phase. Individual task assignments are tracked in the shared GitHub project board.

| Phase / Milestone | Start Date | End Date | Status | Assigned To |
| --- | --- | --- | --- | --- |
| Meet & Plan | 3/10/2026 | 3/18/2026 | Complete | All Members |
| Project Plan Submission | 3/18/2026 | 3/18/2026 | Due | All Members |
| Requirements and Design | 3/19/2026 | 3/25/2026 | Pending | All Members |
| Phase 1 Build – Source Code | 3/25/2026 | 4/01/2026 | Pending | Jamar, Matthew, Mayank |
| Integration and Testing | 4/01/2026 | 4/15/2026 | Pending | All Members |
| Phase 2 Build – Source Code Outline | 4/15/2026 | 4/22/2026 | Pending | Kyle, Joe, Greg |
| Documentation and User Guide | 4/22/2026 | 4/29/2026 | Pending | All Members |
| Final Presentation and Report | 4/29/2026 | 5/5/2026 | Due | All Members |

# 6. Communication Plan

Effective communication is critical to the success of a distributed team project. The following plan outlines the channels, frequency, and responsibilities that will govern how this team shares information, resolves issues, and keeps all members and stakeholders aligned throughout the development process.

## 6.1 Communication Channels

| Communication Type | Channel | Frequency | Responsible |
| --- | --- | --- | --- |
| Weekly Team Meeting | Zoom / Discord | Every Saturday, 11 AM EST | All Members |
| Daily Check-ins | Group Chat (Discord) | Daily (async) | All Members |
| Assignment Updates | UMGC LEO Discussion | As needed | All Members |
| Instructor Communication | UMGC Email / LEO | As needed | Project Manager (Jamar) |
| Code Collaboration | GitHub Pull Requests | Ongoing | All Developers |
| Document Sharing | Google Drive / LEO | Ongoing | All Members |

## 6.2 Meeting Protocol

All weekly Saturday meetings will be conducted via Zoom or Discord at 11:00 AM EST. Each meeting will follow a structured agenda:

- Review of completed tasks since the last meeting

- Status update on in-progress items and any blockers

- Assignment of tasks for the coming week

- Open discussion and Q&A

Meeting notes will be recorded by the Project Manager (Jamar) and shared with all members via the UMGC LEO Group Discussion or Google Drive within 24 hours of the meeting.

## 6.3 Escalation Path

If a team member encounters a blocker that cannot be resolved within 48 hours, the issue should be escalated to the Project Manager. If the issue requires instructor input, the Project Manager will contact the course instructor via UMGC email or the LEO platform on behalf of the team.

## 6.4 Risk Management

The following risks have been identified and mitigation strategies have been established to reduce their potential impact on the project:

| Risk | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Unfamiliarity with tech stack | Medium | High | Schedule dedicated learning sprints; pair experienced with less experienced members. |
| Team availability / scheduling conflicts | Medium | High | Weekly Saturday meetings; async communication via group chat and email. |
| Scope creep | Low | Medium | Maintain a strict scope document; new features require group vote and PM approval. |
| Data loss / version control issues | Low | High | Use GitHub for version control with regular commits and branch protection rules. |
| Integration failures between modules | Medium | High | Conduct integration testing at the end of each build phase before moving forward. |

Risk status will be reviewed at each weekly meeting. New risks will be added to the risk register as they are identified, and mitigation strategies will be updated accordingly.

# References

University of Maryland Global Campus. (2026). CMSC 495: Computer Science Capstone. UMGC Course Materials. https://www.umgc.edu

Oracle Corporation. (2025). Java SE Documentation. https://docs.oracle.com/en/java/

Python Software Foundation. (2025). Python 3 Documentation. https://docs.python.org/3/

SQLite Consortium. (2025). SQLite Documentation. https://www.sqlite.org/docs.html

GitHub, Inc. (2025). GitHub Documentation. https://docs.github.com