UMGC CMSC 495

Computer Science Capstone

Personal Expense Tracker

Project Design Document

Submitted by:

Jamar (Project Manager)

Matthew (Lead Developer)

Kyle (UI/Frontend Developer)

Mayank (UI/Frontend Developer)

Joe (QA Tester / Developer)

Greg (QA Tester / Developer)

Spring 2026

# 1. Project Scope

The Personal Expense Tracker is a locally-hosted Java desktop application developed as the UMGC CMSC 495 capstone project. This section defines the objectives, deliverables, and boundaries that govern the entire development effort.

## 1.1 Objectives

The primary objective of this project is to design and deliver a fully functional desktop expense-tracking application that demonstrates the team's ability to apply software engineering principles collaboratively. Specific objectives include:

- Deliver a working desktop GUI application using JavaFX following the MVC architectural pattern.

- Implement a local SQLite database for secure, offline data persistence.

- Provide expense entry, editing, deletion, categorization, and search capabilities.

- Generate visual spending reports (bar and pie charts) filterable by date range and category.

- Support CSV and JSON data import/export via Python scripts invoked through Java's ProcessBuilder API.

- Produce complete project documentation: user guide, test plan, and final report.

## 1.2 Deliverables

The following deliverables are required to fulfil the course requirements and mark the project complete:

- Project Plan Document (Due: March 18, 2026)

- Project Design Document (Due: March 25, 2026)

- Source Code and Source Code Outline

- User Guide and Test Plan

- Fully functional Personal Expense Tracker desktop application

- Final Report and Presentation (Due: May 5, 2026)

## 1.3 Boundaries and Limitations

In Scope:

- Local user registration and login with hashed password storage

- Full expense CRUD (Create, Read, Update, Delete) operations

- Predefined and custom expense categories

- Dashboard with spending summary and graphical reports

- CSV/JSON import and export functionality

- SQLite database for local, offline data persistence

- User documentation and in-app help reference

Out of Scope:

- Cloud storage or online synchronization of expense data

- Mobile application development (iOS or Android)

- Integration with external banking APIs or financial institutions

- Multi-user or shared account functionality

- Subscription billing or payment processing

- Automated recurring expense tracking

## 1.4 Assumptions and Constraints

- All six team members have access to a personal computer capable of running Java 17+ applications.

- The project must be completed by May 5, 2026, the course's final deadline.

- The application targets Windows 10/11 as the primary platform, with best-effort macOS and Linux compatibility.

- All tools, libraries, and frameworks used are free and open-source.

- No external budget is allocated; all resources are either personally owned or provided by UMGC.

# 2. Project Requirements

Requirements define what the Personal Expense Tracker must do (functional) and the quality standards it must meet (non-functional). All requirements are derived directly from the Project Plan and scoped to the deliverables identified in Section 1.

## 2.1 Functional Requirements

The table below enumerates the functional requirements that the application must satisfy. Each requirement has a unique identifier to support traceability in the test plan.

| ID | Requirement | Description |
| --- | --- | --- |
| FR-01 | User Authentication | The system shall allow users to register a local account and log in with a username and password stored in the SQLite database. |
| FR-02 | Expense Entry | The system shall allow users to add new expense records with fields: date, amount, category, and description. |
| FR-03 | Expense Management | The system shall allow users to edit and delete existing expense records. |
| FR-04 | Category Management | The system shall provide predefined categories (Food, Transportation, Housing, Entertainment, Healthcare, Other) and allow users to create custom categories. |
| FR-05 | Dashboard | The system shall display a dashboard summarizing recent expenses and monthly totals by category. |
| FR-06 | Reporting | The system shall generate bar and pie chart visualizations of spending, filterable by date range and category. |
| FR-07 | Search & Filter | The system shall provide search and filter capabilities across all stored expense records. |
| FR-08 | Data Export | The system shall export expense data to CSV and JSON formats via an integrated Python script invoked through Java ProcessBuilder. |
| FR-09 | Data Import | The system shall import expense data from a correctly formatted CSV file to pre-populate records. |
| FR-10 | Data Persistence | All expense records shall be persisted in a local SQLite database and available across application sessions. |

## 2.2 Non-Functional Requirements

Non-functional requirements define quality attributes and operational constraints that apply across the entire system.

| ID | Category | Requirement |
| --- | --- | --- |
| NFR-01 | Performance | The application shall load the dashboard and render reports in under 2 seconds on standard hardware (Intel Core i5, 8 GB RAM). |
| NFR-02 | Usability | The GUI shall follow standard desktop UI conventions; a new user shall be able to log an expense within 3 minutes of first launch without external guidance. |
| NFR-03 | Reliability | The application shall handle invalid user inputs (non-numeric amounts, missing required fields) gracefully with clear error messages without crashing. |
| NFR-04 | Portability | The application shall run on Windows 10/11 as the primary target, with best-effort support for macOS and Linux via the Java runtime. |
| NFR-05 | Maintainability | All source code shall follow Java naming conventions and include inline comments. Modules shall be separated according to MVC architecture. |
| NFR-06 | Security | User passwords shall be hashed before storage. No plaintext credentials shall be written to the database or log files. |
| NFR-07 | Scalability | The SQLite schema shall support at least 1,000 expense records without degradation in query or render performance. |

# 3. Project Methodology

## 3.1 Chosen Approach: Agile (Scrum-Inspired)

The team will adopt an Agile methodology inspired by the Scrum framework. Work will be organized into two-week iterations (sprints), each culminating in a potentially shippable increment of the application. This approach was chosen for the following reasons:

- Incremental delivery: Breaking the project into two build phases (Phase 1: core features; Phase 2: enhancements) aligns naturally with Agile's iterative philosophy, allowing the team to validate core functionality before building enhancements.

- Adaptability: The team is geographically distributed across different time zones. Agile's lightweight ceremonies (weekly stand-ups, sprint reviews) are well-suited to asynchronous collaboration via Discord and GitHub.

- Transparency: GitHub Issues and a shared project board provide continuous visibility into task status, making it easy to identify blockers early and re-prioritize work.

- Reduced risk of late integration: Continuous integration testing at the end of each sprint prevents large, destabilizing merges that are common in traditional Waterfall projects.

## 3.2 Why Not Waterfall?

We considered a Waterfall methodology but rejected it because it requires all requirements to be fully defined and frozen before development begins. Given that this is a student capstone project with six members across varying experience levels, requirements are likely to be refined as the team learns more about the technology stack. Agile's flexibility accommodates these refinements without requiring a formal change-control process.

## 3.3 Ceremonies and Artefacts

- Weekly Sprint Meeting (Saturday, 11 AM EST via Zoom/Discord): Sprint review of completed work, retrospective, and planning for the next sprint.

- Daily Async Stand-up (Discord): Each member posts a brief status update answering: What did I complete? What will I do next? Are there any blockers?

- GitHub Project Board: Acts as the sprint backlog and Kanban board; tasks move from 'To Do' to 'In Progress' to 'Done'.

- Pull Request Reviews: All code merged to the main branch must pass at least one peer review before merging.

- Sprint Demo: At the end of each phase, the team conducts a live demonstration of completed features to verify they meet acceptance criteria.

## 3.4 MVC Architectural Pattern

The application will be implemented using the Model-View-Controller (MVC) design pattern, consistent with the approach used in the sample project design provided for this course. This separation of concerns ensures maintainability and testability:

- Model: Manages all data operations, including CRUD interactions with the SQLite database via JDBC and business logic such as expense calculations and category management.

- View: Implements all GUI screens using JavaFX, including the login screen, expense entry form, dashboard, reporting charts, and search/filter interface.

- Controller: Handles user events triggered by the View, validates input, and delegates operations to the Model, then updates the View with results.

# 4. Work Breakdown / Project Tasks

The Work Breakdown Structure (WBS) below decomposes the project into seven top-level work packages, each subdivided into specific tasks. Start and end dates align with the schedule in Section 5, and assigned members reflect the roles defined in the Project Plan.

| WBS ID | Task / Deliverable | Start | End | Assigned To |
| --- | --- | --- | --- | --- |
| 1.0 | Project Planning & Setup | 3/10/26 | 3/18/26 | All Members |
| 1.1 | Team kickoff and role assignment | 3/10/26 | 3/12/26 | Jamar |
| 1.2 | Project Plan document | 3/12/26 | 3/18/26 | All Members |
| 1.3 | Set up GitHub repository | 3/12/26 | 3/14/26 | Matthew |
| 1.4 | Configure dev environments | 3/14/26 | 3/18/26 | All Members |
| 2.0 | Requirements & Design | 3/19/26 | 3/25/26 | All Members |
| 2.1 | Finalize functional requirements | 3/19/26 | 3/21/26 | Jamar, Matthew |
| 2.2 | Database schema design (SQLite) | 3/19/26 | 3/22/26 | Matthew |
| 2.3 | MVC architecture design | 3/21/26 | 3/23/26 | Kyle, Mayank |
| 2.4 | Project Design document | 3/23/26 | 3/25/26 | All Members |
| 3.0 | Phase 1 Build – Core Features | 3/25/26 | 4/01/26 | Jamar, Matthew, Mayank |
| 3.1 | User auth module (login/register) | 3/25/26 | 3/28/26 | Matthew |
| 3.2 | Expense CRUD operations | 3/25/26 | 3/30/26 | Jamar, Matthew |
| 3.3 | Main dashboard UI | 3/28/26 | 4/01/26 | Kyle, Mayank |
| 3.4 | SQLite integration | 3/25/26 | 3/28/26 | Matthew |
| 4.0 | Integration & Testing | 4/01/26 | 4/15/26 | All Members |
| 4.1 | Unit testing (JUnit) | 4/01/26 | 4/08/26 | Joe, Greg |
| 4.2 | Integration testing | 4/08/26 | 4/12/26 | All Members |
| 4.3 | Bug fixes and code review | 4/12/26 | 4/15/26 | All Members |
| 5.0 | Phase 2 Build – Enhancements | 4/15/26 | 4/22/26 | Kyle, Joe, Greg |
| 5.1 | Reporting charts (bar/pie) | 4/15/26 | 4/19/26 | Kyle, Mayank |
| 5.2 | CSV/JSON import-export (Python) | 4/15/26 | 4/19/26 | Matthew |
| 5.3 | Search & filter UI | 4/19/26 | 4/22/26 | Kyle, Joe |
| 6.0 | Documentation & User Guide | 4/22/26 | 4/29/26 | All Members |
| 6.1 | User guide | 4/22/26 | 4/26/26 | Joe, Greg |
| 6.2 | Test plan document | 4/22/26 | 4/26/26 | Joe, Greg |
| 6.3 | Source code documentation | 4/26/26 | 4/29/26 | All Members |
| 7.0 | Final Report & Presentation | 4/29/26 | 5/05/26 | All Members |
| 7.1 | Compile final report | 4/29/26 | 5/03/26 | All Members |
| 7.2 | Prepare and rehearse presentation | 5/03/26 | 5/05/26 | All Members |

Note: WBS IDs ending in '.0' denote top-level work packages (summary tasks). Sub-tasks are indented below each parent.

# 5. Project Schedule

The schedule below reflects the milestones derived from the Project Plan and the WBS. All dates represent the end-of-day target for the assigned deliverable. The project spans from March 10, 2026 to May 5, 2026, a total of approximately eight weeks.

| Milestone | Start Date | Target Date | Status | Assigned To |
| --- | --- | --- | --- | --- |
| Project Plan Submission | 3/10/26 | 3/18/26 | Complete | All Members |
| Requirements & Design Complete | 3/19/26 | 3/25/26 | Pending | All Members |
| Phase 1 Build Complete | 3/25/26 | 4/01/26 | Pending | Jamar, Matthew, Mayank |
| Integration & Testing Complete | 4/01/26 | 4/15/26 | Pending | All Members |
| Phase 2 Build Complete | 4/15/26 | 4/22/26 | Pending | Kyle, Joe, Greg |
| Documentation Complete | 4/22/26 | 4/29/26 | Pending | All Members |
| Final Report & Presentation Due | 4/29/26 | 5/05/26 | Pending | All Members |

## 5.1 Dependencies

The following key dependencies exist between milestones:

- Requirements & Design must be complete before Phase 1 Build begins (3/25/26).

- Phase 1 Build must be complete before Integration & Testing begins (4/01/26).

- Integration & Testing must be complete before Phase 2 Build begins (4/15/26).

- Phase 2 Build must be complete before Documentation begins (4/22/26).

- Documentation must be complete before the Final Report & Presentation (4/29/26).

## 5.2 Schedule Risk Buffer

A one-week buffer has been incorporated between the end of Documentation (4/29/26) and the final presentation (5/05/26) to accommodate unexpected delays. Any milestone slipping by more than three days triggers an immediate team review to re-prioritize scope and resources.

# 6. Project Risks

Risk management is an ongoing activity throughout the project lifecycle. The risks below were identified during project planning and will be reviewed at each weekly team meeting. New risks will be added to this register as they are discovered.

| Risk | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Unfamiliarity with tech stack | Medium | High | Dedicated learning sprints; experienced members mentor others; pair-programming sessions. |
| Team availability / scheduling conflicts | Medium | High | Fixed weekly Saturday meetings; daily async Discord check-ins; PM monitors task progress. |
| Scope creep | Low | Medium | Strict scope document maintained; all additions require group vote and PM approval. |
| Data loss / version control issues | Low | High | GitHub with branch protection rules; mandatory PR reviews; regular commits enforced. |
| Integration failures between modules | Medium | High | Integration testing at end of each build phase; continuous integration via GitHub Actions. |
| Key member unavailability | Low | High | Cross-training ensures no single point of failure; roles documented for quick handoff. |
| Performance degradation at scale | Low | Medium | SQLite query optimisation; index key columns; performance benchmarks run in Phase 2 testing. |

Probability and impact are rated on a three-point scale: Low, Medium, or High. Any risk rated High impact, regardless of probability, will have a dedicated mitigation owner assigned within the team.

# 7. Project Evaluation Plan

The evaluation plan establishes the criteria, methods, and success thresholds that will be used to assess whether the project has been completed successfully. Evaluation is conducted continuously throughout the project, not only at the final submission.

## 7.1 Evaluation Criteria and Methods

| Evaluation Area | Criteria | Method | Success Threshold |
| --- | --- | --- | --- |
| Functional Completeness | All FR-01 to FR-10 implemented and passing | Manual feature checklist + JUnit test suite | 100% of functional requirements pass acceptance test |
| Code Quality | Clean, maintainable, well-documented code | Peer code review; static analysis (Checkstyle) | Zero critical issues; all methods commented |
| Test Coverage | Adequate unit and integration test coverage | JUnit + integration test suite | >= 80% code coverage across core modules |
| Performance | Meets NFR-01 response-time target | Manual timing; JVM profiling | Dashboard loads < 2 sec; reports render < 2 sec |
| Usability | Intuitive, accessible GUI | User walkthrough + peer review session | New user completes first expense entry <= 3 min |
| Documentation Quality | Complete user guide and test plan | Instructor rubric + peer review | All rubric criteria met; no missing sections |
| Schedule Adherence | Milestones met on time | PM weekly status tracking | Each milestone delivered by target date |

## 7.2 Continuous Evaluation Activities

In addition to the formal evaluation criteria above, the following ongoing activities support continuous quality assurance:

- Weekly Sprint Reviews: At each Saturday meeting, completed work is demonstrated and compared against the sprint goal and acceptance criteria defined for that iteration.

- GitHub Pull Request Reviews: All code contributions are reviewed by at least one other team member before being merged to the main branch, catching defects early.

- Integration Testing Gates: Each build phase concludes with a mandatory integration testing gate. Work does not advance to the next phase until all integration tests pass.

- Instructor Check-ins: The Project Manager (Jamar) will communicate with the course instructor at key milestones (Project Design submission, mid-project check, final submission) to obtain early feedback and ensure alignment with rubric expectations.

## 7.3 Final Evaluation

The project's final evaluation will be conducted before May 5, 2026. The following artefacts will be submitted and assessed:

- Fully functional Personal Expense Tracker application (executable JAR)

- Complete source code with inline documentation, hosted on GitHub

- User Guide covering installation, configuration, and all core features

- Test Plan with documented test cases mapped to functional requirements FR-01 through FR-10

- Final Report summarizing the project lifecycle, technical decisions, lessons learned, and team contributions

- Live application demonstration covering all in-scope features

Success is defined as meeting all seven evaluation thresholds in Section 7.1 and receiving a passing grade from the course instructor based on the published rubric.

# References

University of Maryland Global Campus. (2026). CMSC 495: Computer Science Capstone. UMGC Course Materials. https://www.umgc.edu

Oracle Corporation. (2025). Java SE 17 documentation. https://docs.oracle.com/en/java/javase/17/

Oracle Corporation. (2025). JavaFX documentation. https://openjfx.io/javadoc/17/

Python Software Foundation. (2025). Python 3 documentation. https://docs.python.org/3/

SQLite Consortium. (2025). SQLite documentation. https://www.sqlite.org/docs.html

GitHub, Inc. (2025). GitHub documentation. https://docs.github.com

Schwaber, K., & Sutherland, J. (2020). The Scrum guide. Scrum.org. https://scrumguides.org

Fowler, M. (2018). Patterns of enterprise application architecture. Addison-Wesley Professional.